## backlog2
| As a/an | I want to… | so that.. | Notes | Priority | Estimation | Status
a | user | start a new Trini Hangman game |  | Select Level and Category | 1 | 1 | 40%
b | user | pause and continue when desired | I can complete a game by being able to start from where I left off |  | 4 | 2 | not started
c | new user | create a personal login with username and password | I can play my game with own account and others can play the same game on my phone with their own personal account |  | 6 | 3
d | admin | create a menu feature which will have hints, music and info |  |  | 2 | 2 | not started
e | game designer | have a help feature which describes how to play the game | my user can clearly understand how to play the game | Update the description in strings.xml | 2 | 1 | 80%
g | game designer | create a rating feature to allow users to rate the game |  | Perhaps place this feature after the user plays the game | 6 | 3
h | player | hear local music playing in the background of the game | the game can be different from others with a local twist | Can use Soca, Calypso etc | 3 | 3 | not started
i | player | have the option of hints for each word or phrase to be spelt. |  |  | 3 | 3 | not started
j | player | see a congratulations message when I spell the word correctly. |  |  | 1 | 1 | not started
k | player | see the correct word presented on the screen after being hanged |  |  | 1 | 1 | not started
l | player | move to higher levels of the Trini Hangman game |  |  | 6 | 5
m | player | gain points for each word spelt correctly |  |  | 6 | 1
n | user | have the option to save or continue game as desired |  |  | 2 | 5 | not started
o | user | exit the game at any time when desired |  |  | 1 | 3 | done
p | game designer | place familiar or popular images of Trinidad and Tobago as the background for the screen for that particular category | it adds to the local feel of the game and overall make it more enjoyable | So for example if the category is music, the background can be an image of a steel pan | 2 | 5 | not started
q | player | be able to differentiate the letters that I have selected already from the ones that I am yet to select from |  |  | 1 | 5 | not started
r | game designer | Create the option for the user to turn off the music when playing the game |  |  | 2 | 5 | not started