## Product backlog
ID | As a/an | I want to… | so that.. | Notes | Priority | Estimation | Status
a | new user | create a personal login with username and password | I can play my game with own account and others can play the same game on my phone with their own personal account |  | 2 | 3
b | user | start a new Trini Hangman game |  | Select Level and Category | 1 | 1
c | game designer | have a feature which describes how to play the game |  | How to feature | 2 | 1
d | game designer | provide information about the game and the author |  | Information feature | 1 | 1
e | game designer | create a rating feature to allow users to rate the game |  | Perhaps place this feature after the user plays the game | 2 | 3
f | player | hear local music playing in the background of the game |  | Can use Soca, Calypso etc | 5 | 3
g | player | have the option of hints for each word or phrase to be spelt. |  |  | 4 | 3
h | player | see a congratulations message when I spell the word correctly. |  |  | 1 | 1
i | player | see the correct word presented on the screen after being hanged |  |  | 1 | 1
j | player | move to higher levels of the Trini Hangman game |  |  | 2 | 5
k | player | gain points for each word spelt correctly |  |  | 4 | 1
l | user | have the option to save or continue game as desired |  |  | 1 | 5
m | user | exit the game at any time when desired |  |  | 1 | 3
n | game designer | place familiar or popular images of Trinidad and Tobago as the background for the screen for that particular category | it adds to the local feel of the game and overall make it more enjoyable | So for example if the category is music, the background can be an image of a steel pan | 3 | 5
o | player | be able to differentiate the letters that I have selected already from the ones that I am yet to select from |  |  | 1 | 5
p | game designer | Create the option for the user to turn off the music when playing the game |  |  | 1 | 5

## Definition of done
id | definition of done
a | when I can login in with a username and password and be able to select options to either start or continue a game
b | when I can select the level and category of game and be able to start playing
c
d
e
f
g
h
id
j
k